## Blad1
Sprint Burndown Chart
Backlog ID | User Stories | Initial Estimate | time axis 2023-08-28 to 2023-10-30
Day 0 | time axis 2023-08-28 to 2023-10-30
1 | Index webpagina | 1 | bar: 2023-08-28
2 | Inlog Venster | 0.5 | 2023-08-29: 0.5
3 | Registratie Venster | 0.5 | 2023-08-29: 0.5
4 | Klant Omgeving | 1 | bar: 2023-08-28 to 2023-09-28
5 | Admin Omgeving | 1
6 | Tabellen Overzicht | 1 | bar: 2023-08-28 to 2023-09-30
7 | Create Klant (Signup) | 2 | bar: 2023-08-28 to 2023-09-29
8 | Read Klant (Login) | 2
9 | Update Klant | 2
10 | Delete Klant | 2
11 | Pincode Login (GPS) | 1
12 | Navigatie Scherm | 2 | bar: 2023-08-28 to 2023-10-02
13 | Functie: Uitloggen | 0.5 | 2023-10-03: 0.5
14 | Zoeken op Coordinaten | 1 | bar: 2023-08-28 to 2023-09-18
15 | Track Location Active? | 0.5
16 | Create Restaurant | 2
17 | Read Restaurant | 2
18 | Update Restaurant | 2
19 | Delete Restaurant | 2
20 | MySQL Database+ | 2 | bar: 2023-08-28 to 2023-09-25
21 | Create Tochten | 2
22 | Read Tochten | 2
23 | Update Tochten | 2
24 | Delete Tochten | 2
25 | Create Tracker | 2
26 | Read Tracker | 2
27 | Update Tracker | 2
28 | Delete Tracker | 2
29 | Create Herberg | 2
30 | Read Herberg | 2
31 | Update Herberg | 2
32 | Delete Herberg | 2
33 | Formulieren | 1 | bar: 2023-08-28 to 2023-09-18
34 | Wireframes | 1 | bar: 2023-08-28 to 2023-10-02
35 | Class Diagram | 1 | bar: 2023-08-28 to 2023-10-01
36 | Entity Relation Diagram | 1 | bar: 2023-08-28 to 2023-10-02
37 | Definition of Fun | 1 | bar: 2023-08-28 to 2023-09-28
38 | Overige Documentatie | 4
39 | Burndown Chart | 1 | bar: 2023-08-28 to 2023-10-02
40 |  | 1
41 |  | 1
Remaining Effort |  | 64 | 63 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 61 | 62 | 59 | 59 | 59 | 59 | 58 | 58 | 58 | 57 | 57 | 57 | 55 | 54 | 53 | 52 | 48 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5 | 47.5
Ideal Trend |  | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Done
In Progress
On Hold...